## Team
Team
Stakeholder | Miroslav Juric
Product Owner | Benjamin Ziegler
Scrum Master | Marc Schöchlin
Developers | Peter Bühler
Lucas Vorpahl
Dennis Hieber

## Release Plan
Release Plan
Release | Start | Days | End | Size | Status | Release | Goal
1 | 2016-02-18 | 29 | 2016-03-17 | 7 | Released | 2016-03-16 | User Stories sammeln und Spezifikation fertigstellen
2 | 2016-03-17 | 29 | 2016-04-14 | 12 | Released | 2016-04-28 | UML Diagramme anfertigen
3 | 2016-04-14 | 15 | 2016-04-28 | 11 | Ongoing | 2016-04-28 | Dokumentation zusammenführen, Präsentation erstellen
Sprint Plan
Sprint | Start | Days | End | Size | Status | Release | Goal | Release
1 | 2016-02-19 | 7 | 2016-02-25 | 1 | Released | 2016-02-18 | Setup Git Repo und Scrum Tool | 1
2 | 2016-02-26 | 32 | 2016-03-28 | 6 | Released | 2016-02-25 | User Stories mit Kunde definieren und Spezi. Erstellen | 1
3 | 2016-03-29 | 23 | 2016-04-20 | 7 | Released | 2016-03-17 | Erste Use Cases modellieren | 2
4 | 2016-04-21 | 9 | 2016-04-29 | 5 | Released | 2016-04-05 | Klassendiagramme und Sequenzdiagramme modellieren | 2
5 | 2016-04-30 | 21 | 2016-05-20 | 11 | Ongoing | 2016-04-14 | Präsentation erstellen | 3
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
|  |  | Unallocated stories | 0
Formulas:
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")
Start = IF(AND([Start, row above]<>"",[Days, row above]<>"",[Days]<>""),[Start, row above]+[Days, row above],"")

## Backlog
Backlog
Backlog ID | Story name | Status | Size | Sprint | Priority | Comments
1 | Git Repo anlegen | Done | 1 | 1 | 4 | Git Repo anlegen um eine Versionskontrolle zu ermöglichen.
2 | SCRUM Tools evaluieren und Konfigurieren | Done | 1 | 1 | 3 | Die verschiedenen möglichen SCRUM Tools sollen untersucht werden und das, am besten in das Projekt passende, herausgesucht und konfiguriert werden.
3 | User Stories definieren | Done | 3 | 2 | 2
4 | Spezifikation aus User Stories erstellen | Done | 3 | 2 | 4
5 | Use Case "Strich hinzufügen" erstellen | Done | 1 | 3 | 5
6 | Use Case "Passwortschutz (de)aktivieren" erstellen | Done | 2 | 3 | 2
7 | Use Case "Benutzerverwaltung" erstellen | Done | 1 | 3 | 3
8 | Use Case "Kostenberechnung" erstellen | Done | 3 | 3 | 4
9 | Klassendiagramm "Coffee Manager" erstellen | Done | 3 | 4 | 5 | Soll die Klassen Strichliste, Benutzer und Strich modellieren
10 | Sequenzdiagramm "Strich hinzufügen" erstellen | Done | 1 | 4 | 5
11 | Sequenzdiagramm "Strichliste bearbeiten" erstellen | Done | 1 | 4 | 3
12 | Informationen für Präsentation zusammentragen | Ongoing | 2 | 5 | 5
13 | Scrumwise Daten exportieren in Excelsheet | Ongoing | 3 | 5 | 5
14 | Präsentation erstellen | Planned | 5 | 5 | 4
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D4: Story Points or Ideal Days
Note on E4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.

## Sp1
1
Setup Git Repo und Scrum Tool
Sprint implementation days | 4 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 4 | Days | Totals | 5 | 4 | 3 | 1
Task rows | 3 | Done days | 3 |  | 5 | 3.75 | 2.5 | 1.25
Warning! These are necessary |  | Trend |  |  | 4.1667 | 2.6667 | 1.1667
template rows |  | Trend Days | 3 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Backlog ID | Responsible | Status | Est. | 4.1667 1: 1; 2.6667 2: 2; 1.1667 3: 3; 1.1667 4: 4
Git Repo anlegen | 1 | Marc Schöchlin | Done | 2 | 4.1667 1: 1; 2.6667 2: 0; 1.1667 3: 0; 1.1667 4: 0
SCRUM Tools evaluieren und Konfigurieren | 2 | Lucas Vorpahl | Done | 2 | 4.1667 1: 2; 2.6667 2: 2; 1.1667 3: 1; 1.1667 4: 0
SCRUM Tools evaluieren und Konfigurieren | 2 | Dennis Hieber | Done | 1 | 4.1667 1: 1; 2.6667 2: 1; 1.1667 3: 0; 1.1667 4: 0
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp2
2
User Stories mit Kunde definieren und Spezi. Erstellen
Sprint implementation days | 10 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 10 | Days | Totals | 6 | 5 | 4 | 4 | 4 | 2 | 1 | 0 | 0 | 0 | 0
Task rows | 4 | Done days | 6 |  | 6 | 5.4 | 4.8 | 4.2 | 3.6 | 3 | 2.4 | 1.8 | 1.2 | 0.6
Warning! These are necessary |  | Trend |  |  | 5.1905 | 4.4476 | 3.7048 | 2.9619 | 2.219 | 1.4762 | 0.73333
template rows |  | Trend Days | 6 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Backlog ID | Responsible | Status | Est. | 5.1905 1: 1; 4.4476 2: 2; 3.7048 3: 3; 2.9619 4: 4; 2.219 5: 5; 1.4762 6: 6; 0.73333 7: 7; 0.73333 8: 8; 0.73333 9: 9; 0.73333 10: 10
User Stories definieren | 3 | Peter Bühler | Done | 2 | 5.1905 1: 1; 4.4476 2: 0; 3.7048 3: 0; 2.9619 4: 0; 2.219 5: 0; 1.4762 6: 0; 0.73333 7: 0
User Stories definieren | 3 | Lucas Vorpahl | Done | 1 | 5.1905 1: 2; 4.4476 2: 2; 3.7048 3: 2; 2.9619 4: 2; 2.219 5: 1; 1.4762 6: 0; 0.73333 7: 0
Spezifikation aus User Stories erstellen | 4 | Dennis Hieber | Done | 2 | 5.1905 1: 1; 4.4476 2: 1; 3.7048 3: 1; 2.9619 4: 1; 2.219 5: 1; 1.4762 6: 1; 0.73333 7: 0
Spezifikation aus User Stories erstellen | 4 | Peter Bühler | Done | 1 | 5.1905 1: 1; 4.4476 2: 1; 3.7048 3: 1; 2.9619 4: 1; 2.219 5: 0; 1.4762 6: 0; 0.73333 7: 0
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp3
3
Erste Use Cases modellieren
Sprint implementation days | 12 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 12 | Days | Totals | 7 | 7 | 4 | 3 | 2 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Task rows | 4 | Done days | 6 |  | 7 | 6.4167 | 5.8333 | 5.25 | 4.6667 | 4.0833 | 3.5 | 2.9167 | 2.3333 | 1.75 | 1.1667 | 0.58333
Warning! These are necessary |  | Trend |  |  | 5.5238 | 4.781 | 4.0381 | 3.2952 | 2.5524 | 1.8095 | 1.0667 | 0.32381
template rows |  | Trend Days | 6 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Backlog ID | Responsible | Status | Est. | 5.5238 1: 1; 4.781 2: 2; 4.0381 3: 3; 3.2952 4: 4; 2.5524 5: 5; 1.8095 6: 6; 1.0667 7: 7; 0.32381 8: 8; 0.32381 9: 9; 0.32381 10: 10; 0.32381 11: 11; 0.32381 12: 12
Use Case "Strich hinzufügen" erstellen | 3 | Dennis Hieber | Done | 1 | 5.5238 1: 1; 4.781 2: 1; 4.0381 3: 1; 3.2952 4: 0; 2.5524 5: 1; 1.8095 6: 0; 1.0667 7: 0
Use Case "Passwortschutz (de)aktivieren" erstellen | 3 | Peter Bühler | Done | 2 | 5.5238 1: 2; 4.781 2: 0; 4.0381 3: 0; 3.2952 4: 0; 2.5524 5: 0; 1.8095 6: 0; 1.0667 7: 0
Use Case "Benutzerverwaltung" erstellen | 4 | Dennis Hieber | Done | 1 | 5.5238 1: 1; 4.781 2: 0; 4.0381 3: 0; 3.2952 4: 0; 2.5524 5: 1; 1.8095 6: 1; 1.0667 7: 0
Use Case "Kostenberechnung" erstellen | 4 | Lucas Vorpahl | Done | 3 | 5.5238 1: 3; 4.781 2: 3; 4.0381 3: 2; 3.2952 4: 2; 2.5524 5: 2; 1.8095 6: 1; 1.0667 7: 0
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp4
4
Klassendiagramme und Sequenzdiagramme modellieren
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 5 | 5 | 4 | 1 | 0 | 0
Task rows | 3 | Done days | 3 |  | 5 | 4 | 3 | 2 | 1
Warning! These are necessary |  | Trend |  |  | 5.3333 | 3.3333 | 1.3333
template rows |  | Trend Days | 3 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Backlog ID | Responsible | Status | Est. | 5.3333 1: 1; 3.3333 2: 2; 1.3333 3: 3; 1.3333 4: 4; 1.3333 5: 5
Klassendiagramm "Coffee Manager" erstellen | 9 | Peter Bühler | Done | 3 | 5.3333 1: 3; 3.3333 2: 3; 1.3333 3: 0; 1.3333 4: 0; 1.3333 5: 0
Sequenzdiagramm "Strich hinzufügen" erstellen | 10 | Lucas Vorpahl | Done | 1 | 5.3333 1: 1; 3.3333 2: 0; 1.3333 3: 0; 1.3333 4: 0; 1.3333 5: 0
Sequenzdiagramm "Strichliste bearbeiten" erstellen | 11 | Dennis Hieber | Done | 1 | 5.3333 1: 1; 3.3333 2: 1; 1.3333 3: 1; 1.3333 4: 0; 1.3333 5: 0
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp5
5
Präsentation erstellen
Sprint implementation days | 10 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 10 | Days | Totals | 11 | 8 | 8 | 8 | 11 | 8 | 0 | 0 | 0 | 0 | 0
Task rows | 3 | Done days | 5 |  | 11 | 9.9 | 8.8 | 7.7 | 6.6 | 5.5 | 4.4 | 3.3 | 2.2 | 1.1
Warning! These are necessary |  | Trend |  |  | 8 | 8.3 | 8.6 | 8.9 | 9.2 | 9.5 | 9.8 | 10.1 | 10.4 | 10.7 | 11 | 11.3 | 11.6 | 11.9 | 12.2 | 12.5 | 12.8 | 13.1 | 13.4 | 13.7 | 14 | 14.3 | 14.6 | 14.9 | 15.2
template rows |  | Trend Days | 5 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Backlog ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7; 8: 8; 9: 9; 10: 10
Informationen für Präsentation zusammentragen | 9 | Lucas Vorpahl | Ongoing | 3 | 1: 3; 2: 3; 3: 3; 4: 3; 5: 2
Scrumwise Daten exportieren in Excelsheet | 10 | Marc Schöchlin | Ongoing | 3 | 1: 0; 2: 0; 3: 0; 4: 3; 5: 1
Präsentation erstellen | 11 | Dennis Hieber | Planned | 5 | 1: 5; 2: 5; 3: 5; 4: 5; 5: 5
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Backlog Burndown
Backlog Burndown Chart
Original planned size |  |  | 137 |  | Sprint count | 5
Count trend from last |  |  | 5 | sprints | Trend sprint count | 3
[5 empty] | Trend offset | 0
Velocity (points per sprint) |  |  |  |  | Sprints in Trend | 3
Original estimate |  |  | 30
5 |  |  | 25
Realized total average |  |  | 25 |  | Trend count | 7
Average last 8 |  |  | 25
Avg. worst 3 in last 8 |  |  | 25
Trend |  |  | 25
These hidden cells are used to draw the graph on this page. DO NOT DELETE!
Predictions - Completion at the end of sprint…
Original estimate - Min |  |  | 3
Original estimate - Avg |  |  | 5
Original estimate - Max |  |  | 8 |  | Standard Dev. | 2.8284
5 |  |  | 6
Realized average |  |  | 6 |  | LastPlanned | 28
Average last 8 |  |  | 6 |  | LastRealized | 0
Avg. worst 3 in last 8 |  |  | 6
Trend |  |  | 6
Realized + St. Dev |  |  | 6
Realized - St. Dev |  |  | 6
[5 empty] | Trend | [7 empty] | Average Speeds
Sprint | Remain.Work | Planned Work | Realized Work | Current Total Size | Col top | Do not delete… |  | Col bottom | Trend Help | Raw Trend | Real Trend | Current Bottom | Realized | Last 8 | Worst 3 in Last 8
1 | 137 | 23 | 23 | 137 | 137 | 137 | 0 | 0 | 137 | 137.6667 | 137.6667 | 0 | 25 | 25 | 25
2 | 114 | 29 | 27 | 137 | 114 | 114 | 0 | 0 | 114 | 112.6667 | 112.6667 | 0 | 25 | 25 | 25
3 | 87 | 31 |  | 137 | 87 | 87 | 0 | 0 | 87 | 87.6667 | 87.6667 | 0 | 25 | 25 | 25
4 | 56 | 28 |  | 137 | 0 | 0 | 56 | 56 | 56 | 62.6667 | 62.6667 | 0 | 25 | 25 | 25
5 | 28 | 28 |  | 137 | 0 | 0 | 28 | 28 | 28 | 37.6667 | 37.6667 | 0 | 25 | 25 | 25
6 | [9 empty] | 12.6667 | 12.6667 | 0 | 25 | 25 | 25
7 | [9 empty] | 0 | 0 | 0 | 25 | 25 | 25
8 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
9 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
10 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
11 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
12 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
13 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
14 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
15 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
16 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
17 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
18 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
19 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
20 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
21 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
22 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
23 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
24 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
Note on B15: Average estimate * 0,6
Note on B17: Average estimate * 1,6
Note on B19: As of latest Product Backlog estimate